ESADE Sustainable Finance

Final Group Assignment

AI-Agent Research Pipeline for Sustainable Portfolio Construction

Project Plan & Role Workflow

Team of 5  |  4-Week Execution Plan  |  Final Submission: 22 May 2026

# 1. Overview

This document is the operating plan for our 5-person team for the ESADE MSc Finance Sustainable Finance group assignment. It defines roles, responsibilities, learning paths, tools, deliverables, and the four-week execution timeline.

All coding work in this project is performed through AI-assisted vibe coding (Claude / ChatGPT). No team member is required to write code from scratch. Instead, each operator learns to direct, run, and verify AI-generated outputs using the workflow defined in Section 3 (Learning Curve & Skill Map).

### Team Composition

- Total members: 5

- Coding baseline: none — all members start as AI-assisted operators

- Mental model: "We do not read code; we verify outputs." Code is generated and debugged by Claude. Humans verify the resulting tables, JSON, and numbers.

### Key Deadlines

- 8 May — One-page Proposal submitted

- 15 May — Prototype Clinic demonstration

- 19 May — Mock Q&A Drill #1

- 21 May — Mock Q&A Drill #2 + Final Rehearsal

- 22 May, 18:15–20:15 — Final Presentation, Demo, and Q&A

### Assessment Weights

- Written Report: 60%

- Presentation + Demo + Q&A: 40%

### Target Outcome

- Primary target: strong A submission

- Stretch target: A+, achieved via the five quality enhancements (Reading Map, Investment Thesis, 8-Test framework, Mock Q&A drill, Demo Plan B)

- Floor protection: A−, secured by completing the Week 1 learning workshops and meeting the 3 May checkpoint

Note: This plan reflects Prof. Bhattacharya's stated intent that students should "build agents with AI, work with AI, not just write with AI." Our no-code, AI-orchestrated approach is consistent with that philosophy and should be framed as such in the IC pitch and AI Use Statement.

# 2. Role Summary

Five roles, each with a clear mission, primary tools, learning tier, and time commitment.

| Role | Mission | Primary Tools | Tier | Time |
| --- | --- | --- | --- | --- |
| Captain | Investment thesis, IC pitch, group decisions | Google Docs, Claude Pro | T0+T1 | ~35h |
| Data Engineer | Quantitative data, factsheet, financial metrics | Sheets, Colab (via Claude) | T0+T1+T2-C | ~32h |
| ESG Specialist | ESG/Climate methodology, Reading Map, EU regulation | Claude Pro, Sheets | T0+T1 | ~32h |
| Pipeline Operator | n8n GUI workflow, agent orchestration, demo | n8n.cloud, Claude Pro | T0+T1+T2-A | ~35h |
| RAG Operator | Claude Projects RAG, 8-test prompt, biodiversity | Claude Projects, Sheets | T0+T1+T2-B | ~33h |

Note: Time totals include Tier-specific learning hours in Week 1. After Week 1, work shifts almost entirely to substantive execution.

# 3. Learning Curve & Skill Map

This section defines exactly what each team member needs to learn — and, equally important, what to avoid spending time on. Time discipline in Week 1 determines the ceiling of the project.

### Mental Model

- Code itself is written by Claude — we verify outputs (tables, numbers, JSON), not source code

- Error messages are pasted directly into Claude — this resolves ~90% of issues

- No syntax memorisation, no library APIs, no algorithms

- What to learn: how to specify a task, and how to verify a result

### Tier 0 — All members (~3h, by 30 April)

| Skill | Why it matters | Resource | Time |
| --- | --- | --- | --- |
| Google Sheets collaboration | Backbone for 50-stock data, ESG scores, verification | Already familiar / 30-min YouTube | 0–1h |
| Google Drive folder management | 12 sections + appendices + data files | Already familiar | 0h |
| Markdown basics | Collaborative report drafting | MarkdownGuide.org | 30 min |
| Claude Pro Projects feature | Each agent = one Project with system prompt + uploaded files | Anthropic docs + 1 hands-on | 1h |
| Basic prompt writing | Communicate tasks clearly to Claude / GPT | Anthropic prompt engineering docs | 1h |

### Tier 1 — All members (~5h, Week 1)

| Skill | Why it matters | Resource | Time |
| --- | --- | --- | --- |
| Intermediate prompt engineering | 8-Test, methodology, thesis all rely on prompt design | Anthropic prompt engineering guide | 2h |
| Running Claude-generated code (mental model) | Copy code into Colab, run, paste output back | 1 hands-on (Captain demonstrates) | 1h |
| Google Colab in browser | Python without local install — yfinance, table outputs | Colab welcome notebook | 1h |
| Error → Claude → fix loop | Handles ~95% of debugging — paste error, get fix, re-run | 1 hands-on | 1h |

Note: Passing Tier 0 and Tier 1 qualifies a member as an AI-assisted operator. We will hold one combined workshop on 30 April (3 hours) to clear both tiers together.

### Tier 2 — Tool owners only (~3–10h each, Weeks 1–2)

Tier 2-A — Pipeline Operator (n8n.cloud)

| Skill | Required? | Resource | Time |
| --- | --- | --- | --- |
| n8n.cloud account + first workflow | Required | n8n Quickstart + 1 YouTube tutorial | 2h |
| AI nodes (OpenAI / Anthropic) connection | Required | n8n AI node docs | 1h |
| HTTP request node + JSON handling | Required | n8n HTTP docs + Claude guidance | 2h |
| Branching / loop nodes | Recommended | On-demand Claude walkthrough | 1h |
| Connecting 8 agents into a workflow | Required (execution) | Claude provides architecture | 2h |
| Demo recording (Loom or OBS) | Required | Loom signup + 1 trial | 1h |

Tier 2-B — RAG Operator (Claude Projects)

| Skill | Required? | Resource | Time |
| --- | --- | --- | --- |
| Multi-PDF upload to Claude Projects (15–20) | Required | Claude help docs | 30 min |
| Per-Project system prompts (incl. 8-Test) | Required | Anthropic prompt eng + Section 9 template | 2h |
| JSON output extraction into Sheets | Required | Claude prompt engineering | 1h |
| Hallucination verification (30% sample) | Required | Manual cross-check vs source PDF | Spread |
| Quote / page citation verification (Q&A prep) | Required | Manual | Spread |

Tier 2-C — Quant work (Data Engineer)

| Skill | Required? | Resource | Time |
| --- | --- | --- | --- |
| yfinance via Colab (Claude provides code) | Required | Single Claude prompt + execution | 1h |
| Sharpe / volatility / drawdown calculation | Required | Claude provides code; output to Sheets | 1h |
| Apps Script Sheets automation | Optional | Claude provides functions on demand | 1h |

### Tier 3 — Do NOT spend time on these

- Memorising Python syntax (Claude writes all code)

- Building LlamaIndex / Chroma / vector databases (Claude Projects replaces this)

- Deep Git / GitHub workflows (Drive sharing is sufficient)

- Algorithms or data structures

- Docker, cloud infrastructure (n8n.cloud handles hosting)

Note: Searches like "how to build an AI agent" online will surface LangChain, Pinecone, Weaviate, and similar — these are all Tier 3 traps for our four-week timeline. Stay disciplined: n8n + Claude Projects is sufficient for this assignment.

### Week 1 Learning Schedule

| Date | Tier | Participants | Activity |
| --- | --- | --- | --- |
| 30 April (Wed) | T0 + T1 combined workshop | All 5 | 3-hour session — clear Claude Pro / Sheets / Colab / Markdown together |
| 1 May (Thu) | T2-A start | Pipeline Operator | n8n.cloud signup + first workflow |
| 1 May (Thu) | T2-B start | RAG Operator | Build first Claude Project + upload first PDF |
| 2 May (Fri) | T2-C start | Data Engineer | First yfinance run in Colab via Claude |
| 3 May (Sat) | T2 integration check | Tool owners (3) | Demo n8n + Claude Projects + Sheets handoff |
| 5 May (Mon) | Sprint begins | All 5 | Week 1 learning closed; substantive work starts |

# 4. AI-Assisted Tooling Stack

All tools selected on three criteria: (a) zero coding required, (b) free or low-cost, (c) learning curve under 10 hours.

### 4.1 Core Stack

| Layer | Tool | Purpose | Cost | Coding |
| --- | --- | --- | --- | --- |
| Orchestration | n8n.cloud | Connect 8 agents in visual workflow | Free tier or $20/mo | None (drag-and-drop) |
| LLM backbone | Claude Pro (1–2 accounts) | Shared across team; Projects feature | $20–40/mo | None |
| RAG engine | Claude Projects | PDF corpus + standardized extraction prompts | Included with Pro | None |
| LLM API | Anthropic API key | Bulk processing in n8n | $30–50 (50 stocks × 8-Test) | None (key only) |
| Quant compute | Google Colab | yfinance, Sharpe, etc. via Claude code | Free | None (paste-and-run) |
| Data backbone | Google Sheets | All metrics, ESG scores, verification table | Free | None |
| File storage | Google Drive | PDF corpus, deliverables, backups | ESADE account | None |
| Report drafting | Google Docs | 12 sections, simultaneous editing | Free | None |
| Demo recording | Loom (or QuickTime) | Plan B pre-recorded video | Free | None |
| Communication | MS Teams + WhatsApp | Faculty channel + day-to-day | ESADE / free | None |

### 4.2 Tools NOT Used

- LlamaIndex — requires Python; Claude Projects achieves the same outcome with no code

- Standalone vector databases (Chroma, Pinecone, Weaviate) — handled internally by Claude Projects

- GitHub repositories — replaced by Drive sharing for our use case

### 4.3 Estimated Costs (full 4 weeks)

| Item | Minimum | Recommended | Maximum |
| --- | --- | --- | --- |
| Claude Pro (1–2 seats × 1 month) | $20 | $40 | $60 |
| Anthropic API credits (bulk processing) | $20 | $40 | $80 |
| n8n.cloud paid tier (if needed) | $0 (free) | $20 | $50 |
| Other (yfinance keys, contingency) | $0 | $10 | $30 |
| Total | $40 | $110 | $220 |

Note: Split across 5 members, the recommended budget is approximately €20 per person. Pipeline Operator should investigate GitHub Student Pack and Anthropic credit promotions in Week 1 to reduce cost.

### 4.4 Tool Ownership

| Tool | Owner | Backup | Access |
| --- | --- | --- | --- |
| n8n.cloud workflow | Pipeline Operator | Captain | All 5 (view) |
| Claude Pro account 1 (primary) | Captain | ESG Specialist | All 5 (shared password) |
| Claude Pro account 2 (engineering) | Pipeline Operator | RAG Operator | Tool owners only |
| Anthropic API key | Pipeline Operator | Captain | Embedded in n8n; rotatable |
| Claude Projects (~12) | RAG Operator | ESG Specialist | All 5 (access) |
| Google Sheets (master data) | Data Engineer | Captain | All 5 (edit) |
| Google Drive shared folder | Captain | Data Engineer | All 5 (edit) |
| Demo video (Plan B) | Pipeline Operator | Captain | Drive + USB + laptop (3-way backup) |

# 5. Role Definitions

## Role 1 — Captain

Group decision-maker. Owns the investment thesis and portfolio rationale. Leads the IC pitch.

### Workflow

Week 1 — Mandate, Thesis v1, learning workshops

- Define mandate (client, benchmark, sustainability objective); draft 3-sentence thesis; lead the 30 April learning workshop

- Output: Mandate v1, Thesis v1, learning checkpoint passed

Week 2 — Proposal integration, Thesis v2

- Consolidate Week 1 outputs from all members; submit one-page proposal on 8 May

- Output: One-page proposal submitted

Week 3 — Portfolio construction

- Decide top 20 holdings + weights + exclusions; finalise thesis

- Output: Final 20-stock portfolio, final thesis

Week 4 — Pitch and Mock Q&A

- Build pitch deck; lead two Mock Q&A drills (19 May, 21 May); deliver final presentation (22 May)

- Output: Final presentation + Q&A defence

### Key Deliverables

- Investment Mandate document

- Investment Thesis Statement (3 sentences)

- Final 20-stock portfolio

- IC pitch deck (8–10 slides)

- Report Sections 1, 2, 9 (jointly with ESG Specialist), 12 — approximately 1,600 words

- Mock Q&A drill facilitation

### Weekly Hours (incl. 2h learning in Week 1)

| Week 1 | Week 2 | Week 3 | Week 4 |
| --- | --- | --- | --- |
| 10h | 8h | 9h | 8h |

## Role 2 — Data Engineer

Owns all quantitative data and the Google Sheets backbone. Operates Tier 2-C (Quant) workflow.

### Workflow

Week 1 — Universe selection + Tier 2-C learning

- Screen 50 stocks from STOXX Europe 600 (sector diversification); learn Colab via Claude-generated yfinance code

- Output: 50-stock universe list; first successful Colab run

Week 2 — Data ingestion (AI-assisted)

- Request Claude for code to pull 5-year price and ESG raw data; execute in Colab; populate Sheets

- Output: Master data spreadsheet + vintage tags

Week 3 — Financial metrics

- Compute Sharpe, volatility, drawdown, beta via Claude-provided code; integrate into Sheets

- Output: Financial metrics table

Week 4 — Factsheet and report

- Design one-page factsheet; compile data dictionary; draft report sections

- Output: Factsheet + Report Sections 3 and 10

### Key Deliverables

- 50-stock universe (Excel/CSV)

- Master data spreadsheet (with vintage tags)

- Financial metrics table

- Data Dictionary (Appendix — required)

- One-page Factsheet (required)

- Report Sections 3, 10 — approximately 1,300 words

- Contribution to Section 11 (data quality limitations)

### Weekly Hours (incl. 4h learning in Week 1)

| Week 1 | Week 2 | Week 3 | Week 4 |
| --- | --- | --- | --- |
| 8h | 10h | 6h | 8h |

## Role 3 — ESG Specialist

Architect of the ESG/climate methodology. Owner of the Reading-to-Section Mapping Matrix and EU regulatory analysis.

### Workflow

Week 1 — Methodology, Reading Map, learning

- Select E/S/G variables; design weighting and normalisation; produce the 10×12 Reading-Section Mapping Matrix

- Output: ESG methodology v1; Reading Map

Week 2 — EU regulation analysis

- Extract key provisions from Taxonomy / SFDR / CSRD; map to 50-stock sectors

- Output: EU regulation summary

Week 3 — ESG scoring + joint Section 9 work

- Score 50 stocks on E/S/G; compute WACI; co-author methodology portion of Section 9

- Output: Scored 50-stock list; climate metrics; Section 9 methodology draft

Week 4 — Report writing + Q&A lead

- Finalise Sections 5, 6, and 9 (joint); lead ESG/regulation answers in Mock Q&A

- Output: Report Sections 5, 6, 9 (joint); Q&A preparation

### Key Deliverables

- Reading-Section Mapping Matrix (10×12)

- ESG methodology document

- EU regulation summary

- ESG scores per stock (50)

- WACI calculation

- Report Sections 5, 6, 9 (joint) — approximately 1,500 words

### Weekly Hours (incl. 2h learning in Week 1)

| Week 1 | Week 2 | Week 3 | Week 4 |
| --- | --- | --- | --- |
| 11h | 7h | 8h | 6h |

## Role 4 — Pipeline Operator

Connects 8 agents (of the 13 specified in the brief) using the n8n.cloud visual workflow. No code is written; all logic is configured through the GUI. Tier 2-A learning required (~10h).

### Workflow

Week 1 — Tier 0/1/2-A learning

- Set up n8n.cloud; learn AI nodes, HTTP request, JSON handling, branching

- Output: Working n8n account; one functional demo node

Week 2 — Build 8 agent nodes

- Request Claude for the architecture; assemble agents in n8n via drag-and-drop

- Output: Connected pipeline (8 nodes + data routing)

Note: Priority 8 agents: Mandate, Data Ingestion, ESG Scoring, Climate, Greenwashing, Document Intelligence, Portfolio Construction, Reporting.

Week 3 — Integration, debugging, prototype clinic

- Run 50-stock universe through the pipeline; resolve failures by passing errors to Claude; demonstrate at the 15 May clinic

- Output: Working end-to-end pipeline

Week 4 — Demo and Plan B video

- Prepare live demo; record 3–5 minute backup video (Loom); finalise Pipeline Diagram and AI Use Statement

- Output: Live demo + pre-recorded backup + diagram + AI Use Statement

### Key Deliverables

- Working n8n workflow (8 agents connected)

- Pipeline Diagram (Appendix — required)

- AI Use Statement (Appendix — required)

- Pre-recorded demo video (Plan B)

- Report Section 4 — approximately 800 words

- Live demo on 22 May

### Weekly Hours (incl. 10h learning in Week 1)

| Week 1 | Week 2 | Week 3 | Week 4 |
| --- | --- | --- | --- |
| 13h | 11h | 8h | 5h |

## Role 5 — RAG Operator

Builds and operates the document intelligence layer using Claude Projects. Owns the Greenwashing 8-Test prompt template and the biodiversity analysis. Tier 2-B learning required (~5h).

### Workflow

Week 1 — Tier 0/1/2-B + corpus collection

- Learn Claude Projects; download 8–10 sustainability reports; set up first project

- Output: Working Claude Projects; first extraction result

Week 2 — RAG system + 8-Test template

- Create ~12 Claude Projects (one per company corpus or per agent role); standardise the 8-Test prompt; first batch run

- Output: 12 Claude Projects + 8-Test template + initial extractions

Week 3 — Case study, biodiversity, verification

- Apply 8-Test framework to a deep case (DWS or VW); compute biodiversity proxy for 50 stocks (ENCORE / WWF / Aqueduct); verify 30% sample manually

- Output: Case study; biodiversity scores; verified table

Week 4 — Section integration + Q&A lead

- Consolidate the team's Section 11 inputs; draft Sections 7 and 8; lead greenwashing/biodiversity answers in Mock Q&A

- Output: Report Sections 7, 8, 11 (consolidated); Q&A preparation

### Key Deliverables

- Document corpus (15–20 PDFs)

- Claude Projects (~12) — the RAG backbone

- Greenwashing 8-Test prompt template

- Per-company extractions (JSON)

- Greenwashing case study

- Biodiversity scores per stock

- Report Sections 7, 8, 11 (consolidated) — approximately 1,400 words

### Weekly Hours (incl. 5h learning in Week 1)

| Week 1 | Week 2 | Week 3 | Week 4 |
| --- | --- | --- | --- |
| 12h | 11h | 8h | 2h |

# 6. Reading-to-Section Mapping Matrix

Prof. Bhattacharya described the mandatory readings as the "intellectual spine" of the course. This matrix assigns each of the 10 mandatory readings to its primary and secondary report sections, ensuring the bibliography supports — rather than decorates — the methodology. ESG Specialist owns this deliverable in Week 1.

| Reading | Primary Section | Secondary | Use |
| --- | --- | --- | --- |
| Edmans (2023) — End of ESG | Sec 1 | Sec 11 | ESG framing critique |
| Berg / Koelbel / Rigobon (2022) | Sec 5 | Sec 11 | Rating divergence; rejection of single-score reliance |
| Bruno / Esakia / Goltz (2022) | Sec 9 | Sec 10 | ESG alpha scepticism |
| Pastor / Stambaugh / Taylor (2021) | Sec 9 | Sec 10 | Green premium equilibrium |
| Pedersen / Fitzgibbons / Pomorski (2021) | Sec 9 | Sec 5 | ESG-Efficient Frontier (weights) |
| Bolton / Kacperczyk (2021) | Sec 6 | Sec 9 | Carbon premium |
| Giglio / Kelly / Stroebel (2021) | Sec 6 | Sec 11 | Climate finance survey |
| Dimson / Karakas / Li (2015) | Sec 11 | Sec 8 | Active ownership and engagement |
| Dasgupta (2021) — Biodiversity | Sec 7 | Sec 6 | Natural capital framework |
| Edmans (2020) — Grow the Pie | Sec 1 | Sec 12 | Purpose and profit framing |

# 7. Investment Thesis Framework

A required Captain deliverable in Week 1. The three-sentence thesis becomes the headline of Slide 1 and the opening of Section 1, and it anchors all Q&A responses.

| # | Sentence Type | Content Requirement | Example |
| --- | --- | --- | --- |
| 1 | The Gap | Where is the mispricing or disclosure gap? | Among European mid-cap industrials, transition capex relative to EU Taxonomy alignment is improving faster than market perception reflects |
| 2 | Our Edge | How does our AI-agent pipeline identify it? | Claude Projects RAG extracts forward-looking capex commitments from sustainability reports and validates them via the 8-Test framework — capturing a transition trajectory missed by ESG vendor data |
| 3 | The Outcome | Expected performance vs benchmark + sustainability impact | WACI 30% lower than STOXX Europe 600; higher Article 8 alignment; comparable risk-adjusted return over 5 years |

### Self-Check Questions (Captain, Weeks 1–2)

- Sentence 1: Is the market actually missing this gap? Is the claim falsifiable?

- Sentence 2: Can we honestly claim that no other process captures this?

- Sentence 3: Is the benchmark comparison expressed in measurable numbers?

- Do all three sentences appear consistently in Slides 1, 7, and 10?

# 8. Greenwashing 8-Test Prompt Template

Drawn directly from Lecture 1 slides. RAG Operator embeds this as the standard prompt across all Claude Projects, applied uniformly to all 50 candidate stocks.

| # | Dimension | What to Extract | Red Flag |
| --- | --- | --- | --- |
| 1 | Specificity | Exact wording of the claim | Vague terms ("committed to sustainability") |
| 2 | Metric | Supporting number | No numeric backing |
| 3 | Baseline | Comparison reference | Baseline absent or cherry-picked |
| 4 | Target | Stated endpoint | No target / non-binding |
| 5 | Time horizon | Achievement date | Distant (e.g. 2050) and unverifiable |
| 6 | Scope | Which division / asset / product | Ambiguous coverage |
| 7 | Verification | External assurance | Self-reported only |
| 8 | Consistency | Capex / lobbying / portfolio behaviour | Claim inconsistent with capital allocation |

### Standard RAG Prompt (paste into Claude Project system prompt)

"You are an ESG forensic analyst. For [COMPANY], analyse the most recent sustainability report and assess each of the 8 greenwashing dimensions. For each dimension provide: (a) direct quote with page number, (b) numerical value or factual statement, (c) red-flag rating (LOW / MED / HIGH / MISSING), and (d) one to two sentences of reasoning. If a dimension has no information, mark it as MISSING — never invent. Output as JSON with 8 fields."

### Verification Protocol

- RAG Operator manually verifies a 30% sample of all extractions

- Items used in watchlist or exclusion decisions are 100% verified, with cross-check by ESG Specialist

- A "Verified" column is maintained in the master sheet for use during Q&A

# 9. Four-Week Integrated Timeline

Learning is concentrated in Week 1; substantive work runs from Week 2 onwards. Handoffs (Section 10) define dependencies between roles.

| Role | Week 1 (29 Apr–3 May) | Week 2 (4–10 May) | Week 3 (11–17 May) | Week 4 (18–22 May) |
| --- | --- | --- | --- | --- |
| Captain | Mandate + Thesis v1 + lead workshops + send extension email | Proposal integration (8 May) | Final portfolio + final thesis | Pitch deck + Mock Q&A + presentation |
| Data Engineer | 50-stock list + Colab learning | Master data + vintage tags | Sharpe / WACI calculations | Factsheet + report sections |
| ESG Specialist | Methodology + Reading Map | EU Taxonomy / SFDR analysis | ESG scores (50) + Section 9 (joint) | Sections 5, 6, 9 + Q&A prep |
| Pipeline Operator | n8n learning + first node | Build 8 agent nodes | 15 May prototype clinic | Demo + Plan B video |
| RAG Operator | Claude Projects + corpus collection | 8-Test prompt + 12 Projects | DWS case + biodiversity | Sections 7, 8, 11 + Q&A prep |

# 10. Handoff Matrix

Cross-role dependencies. Each handoff has a single owner and a defined timing window.

| From | To | What | When |
| --- | --- | --- | --- |
| Captain | All | Mandate + Thesis v1 (3 sentences) | End of Week 1 |
| ESG Specialist | All | Reading-Section Mapping Matrix | End of Week 1 |
| Data Engineer | ESG Specialist | ESG raw data for 50 stocks | Mid Week 2 |
| Data Engineer | Pipeline Operator | Master data CSV format spec | Start of Week 2 |
| ESG Specialist | Pipeline Operator | Scoring formula (n8n implementation logic) | End of Week 2 |
| RAG Operator | Pipeline Operator | 8-Test RAG output JSON format | End of Week 2 |
| Pipeline Operator | Captain | Integrated 50-stock scored output | End of Week 3 |
| Captain | All | Final 20-stock portfolio + final thesis | End of Week 3 |
| All | RAG Operator | Section 11 reflection paragraphs (1–2 each) | Start of Week 4 |
| All | Captain | Individual report section drafts | Start of Week 4 |

# 11. RACI Matrix

R = Responsible (does the work), A = Accountable (final ownership), C = Consulted.

| Deliverable | Captain | Data Eng. | ESG Spec. | Pipeline Op. | RAG Op. |
| --- | --- | --- | --- | --- | --- |
| Mandate document | RA | C | C | C | C |
| Investment Thesis (3-sentence) | RA | C | C | — | C |
| Reading-Section Mapping Matrix | C | — | RA | — | C |
| 50-stock universe | C | RA | C | — | — |
| ESG scoring methodology | C | C | RA | C | — |
| EU regulation summary | — | — | RA | — | — |
| Pipeline architecture (8 nodes) | C | — | C | RA | C |
| Claude Projects + 8-Test template | — | — | C | C | RA |
| Greenwashing case study | C | — | C | — | RA |
| Final portfolio | RA | C | C | C | C |
| Section 9 (Portfolio + methodology) | R | C | R | — | — |
| Section 11 (Critical Reflection — consolidated) | C | C | C | C | RA |
| Factsheet (1-page) | C | RA | C | — | — |
| Pitch deck | RA | C | C | C | C |
| Live demo (22 May) | A | C | C | RA | C |
| Demo Plan B (pre-recorded) | C | — | — | RA | C |
| Mock Q&A drills (19 May, 21 May) | RA | C | R | C | R |

# 12. Mock Q&A Drill Plan

Prof. Bhattacharya has indicated that external practitioners (asset managers, VC, PE) may join the panel. Two structured drills are scheduled to develop IC-pitch-level defensibility.

### Drill #1 — 19 May (Mon), 90 minutes

- Format: Captain delivers 8–10 minute pitch; the other four members challenge from their respective domains (5 minutes each)

- Goal: Surface methodology weaknesses; verify each lead's ability to defend their domain

- Output: List of unanswered questions to address before Drill #2

### Drill #2 — 21 May (Wed), 90 minutes

- Format: Invite one external observer if possible (another ESADE student with finance background); four-member challenge continues

- Goal: All 25 anticipated questions answerable within 30 seconds

- Output: Go/no-go signal for 22 May presentation

### 25 Anticipated Question Categories

| Category | Example Questions | Lead Responder |
| --- | --- | --- |
| Mandate / Thesis | Why this client / benchmark? Summarise the thesis in one sentence. | Captain |
| Universe / Data | Why STOXX 600? On what basis 50 stocks? How are vintage differences handled? | Data Engineer |
| ESG Methodology | How do you address Berg et al. divergence? Justify E/S/G weights. Why no single score? | ESG Specialist |
| Climate | WACI vs absolute emissions? Impact of missing Scope 3? | ESG Specialist |
| Biodiversity | How are ENCORE / WWF combined? How do you avoid "decorative parsley"? | RAG Operator |
| Greenwashing | Which firms failed the 8-Test most? Why are they on watchlist? | RAG Operator |
| Pipeline / AI | How is hallucination controlled? Where does human override occur? AI Use Statement key points? | Pipeline Operator |
| Portfolio | Top holding rationale? Why include X and exclude Y? Concentration risk? | Captain + ESG Specialist |
| Limitations | What would a professional version improve? | RAG Operator (consolidated) |

Note: The brief explicitly asks: "Where did human judgement override the model or AI output?" — three concrete examples must be prepared in advance and rehearsed in Drill #1.

# 13. Demo Plan B (Failure Hedge)

Contingency for the live demo on 22 May. Pipeline demonstration accounts for 10% of the assessment, so failure is not acceptable.

### Risk Scenarios

- n8n.cloud outage or connectivity failure during the session

- RAG produces hallucinated values during live execution

- Inability to answer "where did human judgement override the model?"

### Three-Layer Hedge

Layer 1 — Pre-recorded demo video (Pipeline Operator, Week 4)

- 3–5 minutes: n8n screen + outputs + voice narration (Loom)

- If live fails, switch to recording: "Let me show you the recorded version."

- Three-way backup: USB + Drive + presenter laptop local storage

Layer 2 — Verification table (RAG Operator + ESG Specialist)

- RAG output for all 50 companies × 8-Test, with a column "Verified by [name], [date]"

- 100% verified for items used in watchlist/exclusion decisions; 30% sample for the rest

- This table is the answer to "how do you control hallucination?"

Layer 3 — Three pre-prepared human override examples

- Example A: ESG vendor assigned high score; 8-Test failed → moved to exclusion

- Example B: Pipeline produced WACI outlier; Data Engineer identified unit error → corrected

- Example C: RAG extracted biodiversity claim with no baseline → moved to watchlist

# 14. Operational Risks & Mitigation

Risks specific to the no-coding, AI-orchestrated approach.

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Claude rate limits exceeded (5 simultaneous users) | Pipeline delays | Two Pro accounts + separate API key + staggered work hours |
| API costs exceed budget ($150+) | Cost burden | Validate prompt efficiency in Week 1; design batched 50-stock processing |
| Unverified hallucinations reach final output | Credibility damage; mark deduction | 30% sample verification + 100% on watchlist/exclusion items + Verified column |
| n8n.cloud outage during 22 May presentation | Live demo failure | Plan B pre-recorded video (Section 13, Layer 1) |
| Tier 2 learning incomplete by end of Week 1 | Week 2 work blocked | 3 May Saturday integration check; 1:1 remediation if needed |
| Panel questions our "no coding" approach | Defensibility weakened | Reframe in AI Use Statement as "orchestration over implementation" — aligned with course philosophy |
| Reading Map skipped, citations added late | Bibliography appears decorative | ESG Specialist Week 1 mandatory deliverable; verified at 3 May checkpoint |

# 15. Group Operations

### Meeting Cadence

- 30 April (Wed), 3h evening — combined Tier 0/1 learning workshop

- 3 May (Sat), 2h afternoon — Tier 2 integration check; tools setup confirmed

- Mondays, 90 minutes — progress check, blocker resolution, weekly plan

- Thursdays, 3h sprint — collaborative work session in person

- 19 May and 21 May, 90 min each — Mock Q&A drills

- Ad hoc — when blockers require group decisions

### Tools Setup (Captain to complete in Week 1)

- Microsoft Teams channel (faculty-recommended)

- WhatsApp group (informal communication)

- Google Drive shared folder

- Google Docs (12 report sections)

- Google Sheets (master data)

- Claude Pro accounts (1–2) + API key

- n8n.cloud account

Note: The MS Teams channel must be created in Week 1 — Prof. Bhattacharya specifically referenced it during the lecture and intends to upload interview-related materials there.

# 16. Next Steps

Immediate actions on plan approval:

- 1. Captain — send deadline-extension email to Prof. Bhattacharya on 1–2 May, after group consensus

- 2. Captain — purchase Claude Pro account(s); share credentials with team by 30 April

- 3. Pipeline Operator — register n8n.cloud + obtain Anthropic API key by 1 May

- 4. RAG Operator — create 12 Claude Projects + first PDF upload by 1 May

- 5. Data Engineer — first yfinance run in Colab by 2 May

- 6. ESG Specialist — Reading-Section Mapping Matrix by end of Week 1

- 7. Captain — Investment Thesis v1 (3 sentences) by end of Week 1

- 8. All — 3 May (Sat) integration check; verify Tier 0/1/2 completion

Note: This is a living document. Update it during weekly Monday meetings to reflect progress and rebalance work as needed. Section reassignment is acceptable when justified by capacity or quality concerns.

— END —